## Slide 1: <PROJECT_TITLE> report <MONTH> <YEAR>
<CREATION_DATE>

## Slide 2: <PROJECT_TITLE> Report – <MONTH> <YEAR>
SUMMARY
The <MILL_NAME> reline was scheduled for <MONTH> <START_DAY>-<END_DAY>.

## Slide 3: High Level Summary of Delays
The <TOTAL_DELAY_HOURS>-hour delay was primarily caused by :
Manually fill in summary.

## Slide 4
Delays by Type

## Slide 5: Recommendations
  The following should be prepared in advance of future relines:
  Prioritize preparation:
    Draining mill, critical parts / tools staged. Crew ready to work on the morning of the first day. 5
  Load level: personnel are trained on setting the ideal load level. This pays dividends for inching throughout the project.
  Ownership of critical equipment: inch drive, adjust-a-veyor, thunderbolt.
    PMs completed in advance, critical spares available.
  Ensure efficient shift change
    Hot change if possible
    Stagger breaks

## Slide 6: Summary of Major Delays
PHASE | TASK | DELAY (HRS) | Type | NOTES

## Slide 7: phase level delay breakdown

## Slide 8: Reline Phases
  Each reline phase and their delays:
No. | PHASE | PHASE DELAY (HRS) | CUMULATIVE DELAY (HRS) | RATIONALE

## Slide 9: Reline Progress

## Slide 10: Reline Phases & Their Delays

## Slide 11: INCHING

## Slide 12: Inching Performance

## Slide 13: Time to First Inch – Day vs Night
Time to first inch was measured as the difference between the shift start time (7:00 AM days, 7:00PM nights) and the first time the inch drive starts for each shift.

## Slide 14: Detailed delay analysis

## Slide 15
Phase <phase_num>: <phase_name> - Timeline

## Slide 16: Phase <phase_num>: <phase_name> Delayed Tasks
TASK NAME | PLANNED DURATION | ACTUAL DURATION | DELAY (HRS) | NOTES
Delay - waiting for load level | 0.0 | 4.6 | 4.6 | Challenges getting load level set. Even with delays, the load level was arguably too high, which hindered progress moving forward.
Delay - scanning mill | 0.0 | 0.3 | 0.3 | Scanning of the mill was not factored into the original schedule. This was an additional 0.3-hour delay.
Planned Duration (hrs) | Actual Duration (hrs)
2.0 | 6.9

## Slide 17: Appendix

## Slide 18
Delays by Type – Raw Data
DELAY TYPE | COUNT | FREQUENCY OF OCCURRENCE | TOTAL DELAY (HRS) | PERCENTAGE OF TOTAL DELAY
General |  |  |  | 
Found Work |  |  |  | 
Preparation |  |  |  | 
Equipment Failure / Unavailability |  |  |  | 
Safety |  |  |  | 
Manpower Shortage |  |  |  |